Assignment 2 Group Plan

MIE354 - Assignment 2

Group Number: 4

Anjali Jammulamadaka

Shreya Perumal

1.0 Introduction

In Assignment 1, a Business Process Diagram, accompanied by a report, was completed for Coorest, a company that enables B2B and B2C ownership of carbon tokens. This assignment requires the group to further analyze the business process by developing the choreography and a description/report to accompany. The following document outlines the necessary steps required to meet deliverable objectives.

2.0 Stages

Stage 0: Assignment Planning and Preparation

- Develop a plan to complete the assignment

- Delegate tasks of different stages and organize them into a timeline

- Both members must post the document to Quercus Discussion

Stage 1: Draft Visio Choreography and Submission Document

- Determine the Choreography and roughly outline

- Draft Visio

- Draft Report

- Review Draft; add/remove/modify sections as required

- Polish and Complete Report

Stage 2: Feedback and Revisions

- Review Deliverables (Report & Visio) against the rubric and assess

- Complete Revisions based on the assessment

- Submit Visio Choreography and Report

3.0 Deliverables

In this assignment, the group is required to submit two key deliverables: 1) BMPN Choreography and 2) Business Choreography Report. The report contains several sections related to the analysis of the Business Process, all of which are outlined below.

Report Breakdown:

1.0 Choreography Objectives, Scope, and Participants

2.0 Declaration regarding the use of Generative AI tools

3.0 Textual Description of the Choreography

4.0 Resource Classification Description for your fully described BP

5.0 Activity Table (with descriptions updated from A1 to reflect your A2 choreography implementation, adding a column to the table to indicate the Participant)

6.0 Justification for the use of the registry blockchain smart contract, including a detailed description of the string content of the keys in the registry

7.0 Generative AI Documentation

8.0 References (if any)

4.0 Task Breakdown and Timeline

To better organize the internal deadlines and manage the tasks delegated to each member, the following Excel table was created. The spreadsheet also features a status tracker to confirm when objectives are met.

Table 1: Task Breakdown and Assignment Timeline (Spreadsheet Linked)

| Stage | Task | Description | Assigned To | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 0 | Creating Group Plan | Creating document outlining the plan for A2 from Stage 0 to Final Submission | Group | 10/22/2025 9:00 PM | Complete |
| 0 | Creating Timeline | Delegate tasks of different stages and organize them into a timeline | Group | 10/22/2025 9:00 PM | Complete |
| 0 | Post Document | Post Group Plan document to Discussion Board | Group | 10/22/2025 9:00 PM | Complete |
| 1 | Draft Choreo | Review Choreography as group and simply draw and outline general idea | Group | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 1.0 | Write up Choreography Objectives, Scope, and Participants | Shreya | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 2.0 | From Assignment Document include the required AI use declaration as in A1 | Anjali | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 3.0 | Write up a textual description of the choreography | Shreya | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 4.0 | Write up overview of all resources utilized in the business process | Shreya | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 5.0 | Writeup/Update Activity Table from A1 | Anjali | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 6.0 | Write up justification for the use of the registry blockchain smart contract, including a detailed description of the string content of the keys in the registry | Shreya | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 7.0 | Document AI prompts used | Anjali | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Section 8.0 | Document sources if used | Shreya | 11/05/2025 11:59 PM | Not Complete |
| 1 | Rough Draft Visio Choreography | Using Visio complete a rough version of the choreoraphy for the business process, with the choreo draft and text as a guide | Anjali | 11/05/2025 11:59 PM | Not Complete |
| 1 | Finalize Section 1-8 | Go through the rough draft and ensure all sections are fully written and complete | Shreya | 11/07/2025 11:59 PM | Not Complete |
| 1 | Finalize Visio Choreography | Ensure the visio is complete | Group | 11/07/2025 11:59 PM | Not Complete |
| 1 | Polish & Complete Visio/Report | Review completed sections, edit and clean up | Group | 11/07/2025 11:59 PM | Not Complete |
| 2 | Asses Visio against rubric | Review Visio and compare against rubric requirements and make note on what needs to be changed | Anjali | 11/09/2025 11:59 PM | Not Complete |
| 2 | Asses Report against rubric | Review Report and compare against rubric and take note of what needs to be changed | Shreya | 11/09/2025 11:59 PM | Not Complete |
| 2 | Complete Revisions | Based on the notes created when compared against the rubrics, complete edits | Group | 11/09/2025 11:59 PM | Not Complete |
| 2 | Submit Visio and Report | Put Visio and Report into the zip folder as described in the assignment information document and submit documents | Group | 11/09/2025 11:59 PM | Not Complete |

5.0 Conclusion

The document outlines the required steps and stages necessary for completing the choreography of the previously analyzed business process. It is estimated that the goals outlined in this document will enable the group to complete desired deliverables prior to final deadlines, ensuring timeliness, organization and a well-executed assignment.