Assignment 1 Group Formation and Plan

MIE354 - Assignment 1

Group Number: 4

Anjali Jammulamadaka 1009931870

Shreya Perumal 1010207107

1.0 Introduction

The following document outlines the plan for Assignment 1 of MIE354. This assignment requires the team to understand and analyze a selected Company’s Business Process and create a model. This document describes the key stages of the assignment, assigns tasks to group members, and highlights crucial internal deadlines and the timeline of activities. It will support the team in meeting their assignment objectives.

2.0 Stages

In the stage breakdowns below, each stage is accompanied by the tasks that must be completed to accomplish each deliverable in each stage. The next section features a timeline connecting people, tasks, deadlines and deliverables.

Stage 0: Assignment Planning and Preparation

- Develop a plan to complete the assignment

- Delegate tasks of different stages and organize them into a timeline

- Both members must post the document to Quercus Discussion

Stage 1: Business Process Selection

- Conduct research on possible Business Processes to select and note relevant URLs

- Write a description of the selected Business Process (Paragraph 1)

- List the name of the organization that owns BP and all external organizations (min 2) that interact with BP (Paragraph 2)

- Post to Quercus Discussion

Stage 2: Draft Diagrams and Submission Document

- Understand the Business Process as a group

- Analyze the Business Process and make notes on key features individually, and compare

- Draft Report (jot note form)

- Draft BPMN Diagram (by hand)

- Review 1: Ensure document adheres to assignment guidelines and rubric

- Get feedback from TAs on specific sections

- Revision 1: As a group, go through the document and edit sections together

- Complete Report Rough Draft (broken up by section)

- Complete BPMN Rough Draft (using Visio)

Stage 3: Feedback and Revisions

- Review 2: Ensure deliverable meets complete expectations and compare with the rubric

- Get feedback on completed deliverables

- Revision 2: As a group, go through the document and edit sections together

- Final readthrough (group)

- Submit Word Document & Visio Diagram

3.0 Deliverables

In this assignment, the group is required to submit two key deliverables: 1) BMPN Diagram and 2) Business Process Report. The report contains several sections related to the analysis of the Business Process, all of which are outlined below.

Report Breakdown:

0.0 Declaration of Generative AI Usage

1.0 Objectives, Customer, and Values

- Identifies the objective of the process as well as the owner organization, the customer, and the value.

2.0 Web References

- An explanation of the use of the sources selected and a list of the URLs

3.0 Process Scope and Process Instance

- Describes the scope and instances of the selected BP

4.0 Textual BP Description

- Describes the coordination of all the BP activities from the perspective of the BP owner

5.0 Registry Use Description and Examples

- Description of what the key and owner strings in the registry represent, and who the owners of the items are, giving concrete examples of keys and owners.

6.0 Resource Classification Description

- Describe the resource classification criteria and the resource classes used to label lanes and/or sub-lanes in the Visio BPMN model, potentially including software packages

7.0 Activity

- Creation of an Activity Table that matches the labels in the Visio BPMN diagram

8.0 Conclusion

4.0 Task Breakdown and Timeline

To better organize the internal deadlines and manage the tasks delegated to each member, the following Excel table was created. The spreadsheet also features a status tracker to confirm when objectives are met.

Table 1: Task Breakdown and Assignment Timeline (Spreadsheet Linked)

| Stage | Task | Description | Assigned To | Deadline | Not Complete |
| --- | --- | --- | --- | --- | --- |
| 0 | Creating Group Plan | Creating a document outlining the plan for A1 from Stage 0 to Final Submission | Group | 10/6/2025 23:59:00 | Complete |
| 0 | Creating Timeline | Delegate tasks of different stages and organize them into a timeline | Group | 10/6/2025 23:59:00 | Complete |
| 0 | Post Document | Post the Group Plan document to the Discussion Board | Group | 10/6/2025 23:59:00 | Complete |
| 1 | Select BP | Conduct research on possible Business Processes to select and keep relevant URLs | Group | 10/7/2025 23:59:00 | Complete |
| 1 | Paragraph 1 | Write a description of the selected Business Process | Shreya | 10/7/2025 23:59:00 | Complete |
| 1 | Paragraph 2 | List the name of the organization that owns BP and all external organizations (min 2) that interact with BP | Anjali | 10/7/2025 23:59:00 | Complete |
| 1 | Discussion Post | Post Paragraphs to Discussion Board | Anjali | 10/8/2025 23:59:00 | Complete |
| 2 | Understand BPMN | Understand the Business Process as a group | Group | 10/9/2025 23:59:00 | Complete |
| 2 | Analyze BP | Analyze the Business Process and make notes on key features | Group | 10/9/2025 23:59:00 | Complete |
| 2 | Report Outline | Draft Report Outline (jot note form) | Group | 10/9/2025 23:59:00 | Complete |
| 2 | BPMN Diagram Draft | Draft the BPMN diagram by hand | Group | 10/9/2025 23:59:00 | Complete |
| 2 | Review 1 | Ensure document adheres to assignment guidelines and rubric | Shreya | 10/9/2025 23:59:00 | Complete |
| 2 | Get Feedback | Get feedback from TAs on specific sections | Group | 10/10/2025 23:59:00 | Not Complete |
| 2 | Revision 1 | As a group, go through the document and edit sections together | Group | 10/10/2025 23:59:00 | Not Complete |
| 2 | RD: Objectives, Customer, and Value | Objectives, Customer, and Value | Anjali | 10/11/2025 23:59:00 | Not Complete |
| 2 | RD: Web References | (the list of requested URLs providing pointers to the source material) and an explanation for the use of sources | Shreya | 10/11/2025 23:59:00 | Not Complete |
| 2 | RD: AI Declaration | Declaration regarding the use of Generative AI tools | Group | 10/11/2025 23:59:00 | Not Complete |
| 2 | RD: Process Scope + Instance | Process Scope and Process Instance | Anjali | 10/11/2025 23:59:00 | Not Complete |
| 2 | RD: BP Description | Textual BP Description | Group | 10/11/2025 23:59:00 | Not Complete |
| 2 | RD: Registry Use Description and Examples | Describe the resource classification criteria and the resource classes used to label lanes and/or sub-lanes in the Visio BPMN model, potentially including software packages | Shreya | 10/11/2025 23:59:00 | Not Complete |
| 2 | Activity Table | This section has a table with 5 headers for the activity Label (matching the labels used in the BPMN Visio diagram), Description (a longer activity description matching the Textual BP Description), Resources (matching the Resource Classification Description), Data Items In, and Data Items Out | Group | 10/11/2025 23:59:00 | Not Complete |
| 2 | BPMN Rough Draft | Create a BPMN Diagram in Visio (Rough Draft) | Anjali | 10/11/2025 23:59:00 | Not Complete |
| 3 | Review 2 | Ensure deliverable complete expectations and compare with the rubric | Anjali | 10/11/2025 23:59:00 | Not Complete |
| 3 | Get Feedback | Get feedback on completed deliverables | Group | 10/11/2025 23:59:00 | Not Complete |
| 3 | Revision 2 | As a group, go through the document and edit sections together | Group | 10/12/2025 23:59:00 | Not Complete |
| 3 | Group Readthorugh | Readthrough document and complete final check | Group | 10/12/2025 23:59:00 | Not Complete |
| 3 | Final Submission | Submit Word Document & Visio Diagram | Shreya | 10/14/2025 23:59:00 | Not Complete |

5.0 Conclusion

The document outlines the required steps and stages necessary for completing a Business Process Diagram for a particular process and its associated report. It is estimated that the goals outlined in this document will enable the group to complete desired deliverables prior to final deadlines, ensuring timeliness, organization and a well-executed assignment.